## Folio1 Timelime
Key | Color
Completed
Scheduled
Estimates Completion
Dealine
Tasks: | Week1 | Week2 | Week3 | Week4 | Week5 | Break | Week6 | Week7 | Week8 | Week9 | Week10 | Week11
Choose Folio Focus
Concept proposal
Research Report
Timeline
Moodboard
Audio Feature list
Visaul Feature list
Relection Form
Asset Management system
Development Documentation
Scene Creation
Folio Assembly
Visual Asset Development
Buidling
Car
Tree
Character
Audio Asset Development
Car
Car engine
Wind
Grass
footsteps(character)
tree
building
Dialogue-welcome
Teleport
Environment Theme
Menu select
Canvas select
Object pick
Object drop
Dialogue-Tutorial
Color ball
Dealine
Folio Milestone Submissions |  |  |  | 2018-08-03 |  |  |  | 2018-08-31 |  |  |  | 2018-09-28

## Folio2 Timelime
Key | Color
Milestone complete
Final Completed
Scheduled
Estimates Completion
Dealine
Tasks: | Week1 | Week2 | Week3 | Week4 | Week5 | Break | Week6 | Week7 | Week8 | Week9 | Week10 | Week11
Choose Folio Focus
Concept proposal
Research Report
Timeline
Moodboard
Audio Feature list
Visaul Feature list
Relection Form
Asset Management system
Development Documentation
Scene Creation
Folio Assembly
Visual Asset Development
Buidling
Car
Tree
Character
Audio Asset Development
Car
Car engine
Wind
Grass
footsteps(character)
tree
building
Dialogue-welcome
Teleport
Environment Theme
Menu select
Canvas select
Object pick
Object drop
Dialogue-Tutorial
Color ball
Dealine
Folio Milestone Submissions |  |  |  | 2018-08-03 |  |  |  | 2018-08-31 |  |  |  | 2018-09-28

## Final Folio
Key | Color
Milestone complete
Final Completed
Scheduled
Estimates Completion
Dealine
Cancelled
Tasks: | Week1 | Week2 | Week3 | Week4 | Week5 | Break | Week6 | Week7 | Week8 | Week9 | Week10 | Week11
Choose Folio Focus
Concept proposal
Research Report
Timeline
Moodboard
Audio Feature list
Visaul Feature list
Relection Form
Asset Management system
Development Documentation
Scene Creation
Folio Assembly
Visual Asset Development
Buidling
Car
StreetLight
Character
Audio Asset Development
Car
Car engine
Wind
Grass
footsteps(character)
tree
building
Dialogue-welcome
Teleport
Environment Theme
Menu select
Canvas select
Object pick
Object drop
Dialogue-Tutorial
Color ball
Dealine
Folio Milestone Submissions |  |  |  | 2018-08-03 |  |  |  | 2018-08-31 |  |  |  | 2018-09-28